## Angular Task
SCHOOL APP Task Sheet
|  | Developer Name: | Role
|  | Mr. Nivas | Java Developer | Server Side API
|  | Mrs. Varsha | Android | Teacher & Parent App Design
|  | Mr. Tushar | Angular | Font End Design
|  | Mr. Lokesh | Designer & Project Manager
|  | Mr. Atul | Team Leder
Task Id | Task Name | Description | More Details | design dead line | Status | API Link | Description | API data dead line | Status
1 | Class & Div | add class | Add class With Div and Class Teacher | 2018-03-29
|  | list class |  | 2018-03-29
|  | edit class |  | 2018-03-29
|  | delete class |  | 2018-03-29
|  | add div |  | 2018-03-29
|  | list div |  | 2018-03-29
|  | edit div |  | 2018-03-29
|  | delete div |  | 2018-03-29
2 | Teacher | add Teacher |  | 2018-03-28
|  | edit Teacher |  | 2018-03-28
|  | list Teacher |  | 2018-03-28
|  | delete Teacher |  | 2018-03-28
3 | Student | add Student | Must Have Class,Div,Gardean Teacher,Parent and other details | 2018-03-30
|  | edit Student |  | 2018-03-30
|  | list Student |  | 2018-03-30
|  | delete Student |  | 2018-03-30
4 | Home Work | Add home work | By Class , Div, Subject | 2018-03-31
|  | list home work |  | 2018-03-31
5 | Time Table | create Time Table | By Class , Div | 2018-03-31
|  | View Time Table |  | 2018-03-31
6 | Gallery | Add Album |  | 2018-03-25
|  | List Album |  | 2018-03-25
|  | Edit Album |  | 2018-03-25
|  | delete Album |  | 2018-03-25
|  | Upload Image | Must have Album | 2018-03-25
|  | View Image By Album |  | 2018-03-25
|  | Remove Image |  | 2018-03-25
7 | Libarary | Add Type |  | 2018-03-26
|  | Edit Type |  | 2018-03-26
|  | List Type |  | 2018-03-26
|  | Delete Type |  | 2018-03-26
|  | Add Subject |  | 2018-03-26
|  | Edit Subject |  | 2018-03-26
|  | List Subject |  | 2018-03-26
|  | Delete Subject |  | 2018-03-26
|  | Add Book | Must have Type And Subject | 2018-03-27
|  | Edit Book |  | 2018-03-27
|  | List Book |  | 2018-03-27
|  | Delete Book |  | 2018-03-27
8 | Result | Add Result | Result of Student By Class and Div | 2018-04-01
|  | list Student and Then Result |  | 2018-04-01
|  | edit Result |  | 2018-04-01
|  | Remove Result of Student By Class and Div |  | 2018-04-01
9 | Attendance | View Attendance | Attendance By Class & div | 2018-04-03
|  | Edit Attendance |  | 2018-04-03
10 | Driver | add Driver |  | 2018-03-21
|  | edit Driver |  | 2018-03-21
|  | list Driver |  | 2018-03-21
|  | Delete Driver |  | 2018-03-21
11 | Bus | add Bus | Have Driver | 2018-03-24
|  | edit Bus |  | 2018-03-24
|  | list Bus |  | 2018-03-24
|  | Delete Bus |  | 2018-03-24
12 | Stops | Add Stop |  | 2018-03-22
|  | List Stop |  | 2018-03-22
|  | Edit Stop |  | 2018-03-22
|  | Delete Stop |  | 2018-03-22
13 | Route | Add Route | Route Must Have asign bus and Driver and multiple stops | 2018-03-23
|  | edit Route |  | 2018-03-23
|  | List Route |  | 2018-03-23
|  | Delete Route |  | 2018-03-23
Tushar Upadhyay Daily Task Status
Task Id | Task Name | Description | More Details | design dead line | Status | Hours
1 | Login | Added the role | Changed the UI, maintained the session for the user | 2018-03-19 | Completed | 2
2 | Navigation Bar | Based on Role Options are filtered | Added new modules | 2018-03-20 | Completed | 2
3 | Dashboard | Based on Role Tabs are filtered | Added new tabs according to the role | 2018-03-20 | Completed | 2
4 | Driver Module | add Driver | Changed Form layout | 2018-03-21
|  | edit Driver |  | 2018-03-21
|  | list Driver |  | 2018-03-21
|  | Delete Driver |  | 2018-03-21

## Android Task
SCHOOL APP Task Sheet
|  | Developer Name: | Role
|  | Mr. Nivas | Java Developer | Server Side API
|  | Mrs. Varsha | Android | Teacher & Parent App Design
|  | Mr. Tushar | Angular | Font End Design
|  | Mr. Lokesh | Designer & Project Manager
|  | Mr. Atul | Team Leder
Task Id | Task Name | Description | More Details | design dead line | Status | API Link | Description | API data dead line | Status
1 | Class & Div | add class | Add class With Div and Class Teacher | 2018-09-03 |  |  |  | 2018-09-03
|  | list class |  | 2018-09-03 |  |  |  | 2018-09-03
|  | edit class |  | 2018-09-03 |  |  |  | 2018-09-03
|  | delete class |  | 2018-09-03 |  |  |  | 2018-09-03
|  | add div |  | 2018-09-03 |  |  |  | 2018-09-03
|  | list div |  | 2018-09-03 |  |  |  | 2018-09-03
|  | edit div |  | 2018-09-03 |  |  |  | 2018-09-03
|  | delete div |  | 2018-09-03 |  |  |  | 2018-09-03
2 | Teacher | add Teacher |  | 2018-09-03 |  |  |  | 13/03/2018
|  | edit Teacher |  | 2018-09-03 |  |  |  | 13/03/2018
|  | list Teacher |  | 2018-09-03 |  |  |  | 13/03/2018
|  | delete Teacher |  | 2018-09-03 |  |  |  | 13/03/2018
3 | Student | add Student | Must Have Class,Div,Gardean Teacher,Parent and other details | 2018-09-03 |  |  |  | 13/03/2018
|  | edit Student |  | 2018-09-03 |  |  |  | 13/03/2018
|  | list Student |  | 2018-09-03 |  |  |  | 13/03/2018
|  | delete Student |  | 2018-09-03 |  |  |  | 13/03/2018
4 | Home Work | Add home work | By Class , Div, Subject | 2018-09-03 |  |  |  | 13/03/2018
|  | list home work |  | 2018-09-03 |  |  |  | 13/03/2018
5 | Time Table | create Time Table | By Class , Div | 2018-10-03 |  |  |  | 14/03/2018
|  | View Time Table |  | 2018-10-03 |  |  |  | 14/03/2018
6 | Gallery | Add Album |  | 2018-10-03 |  |  |  | 14/03/2018
|  | List Album |  | 2018-10-03 |  |  |  | 14/03/2018
|  | Edit Album |  | 2018-10-03 |  |  |  | 14/03/2018
|  | delete Album |  | 2018-10-03 |  |  |  | 14/03/2018
|  | Upload Image | Must have Album | 2018-10-03 |  |  |  | 14/03/2018
|  | View Image By Album |  | 2018-10-03 |  |  |  | 14/03/2018
|  | Remove Image |  | 2018-10-03 |  |  |  | 14/03/2018
7 | Libarary | Add Type |  | 2018-10-03 |  |  |  | 15/03/2018
|  | Edit Type |  | 2018-10-03 |  |  |  | 15/03/2018
|  | List Type |  | 2018-10-03 |  |  |  | 15/03/2018
|  | Delete Type |  | 2018-10-03 |  |  |  | 15/03/2018
|  | Add Subject |  | 2018-10-03 |  |  |  | 15/03/2018
|  | Edit Subject |  | 2018-10-03 |  |  |  | 15/03/2018
|  | List Subject |  | 2018-10-03 |  |  |  | 15/03/2018
|  | Delete Subject |  | 2018-10-03 |  |  |  | 15/03/2018
|  | Add Book | Must have Type And Subject | 2018-10-03 |  |  |  | 15/03/2018
|  | Edit Book |  | 2018-10-03 |  |  |  | 15/03/2018
|  | List Book |  | 2018-10-03 |  |  |  | 15/03/2018
|  | Delete Book |  | 2018-10-03
8 | Result | Add Result | Result of Student By Class and Div | 2018-11-03 |  |  |  | 15/03/2018
|  | list Student and Then Result |  | 2018-11-03 |  |  |  | 15/03/2018
|  | edit Result |  | 2018-11-03 |  |  |  | 15/03/2018
|  | Remove Result of Student By Class and Div |  | 2018-11-03 |  |  |  | 15/03/2018
9 | Attendance | View Attendance | Attendance By Class & div | 2018-11-03 |  |  |  | 16/03/2018
|  | Edit Attendance |  | 2018-11-03 |  |  |  | 16/03/2018
10 | Driver | add Driver |  | 2018-11-03 |  |  |  | 16/03/2018
|  | edit Driver |  | 2018-11-03 |  |  |  | 16/03/2018
|  | list Driver |  | 2018-11-03 |  |  |  | 16/03/2018
|  | Delete Driver |  | 2018-11-03 |  |  |  | 16/03/2018
11 | Bus | add Bus | Have Driver | 2018-12-03 |  |  |  | 16/03/2018
|  | edit Bus |  | 2018-12-03 |  |  |  | 16/03/2018
|  | list Bus |  | 2018-12-03 |  |  |  | 16/03/2018
|  | Delete Bus |  | 2018-12-03 |  |  |  | 16/03/2018
16/03/2018
12 | Stops | Add Stop
List Stop
Edit Stop
Delete Stop
13 | Route | Add Route | Route Must Have asign bus and Driver and multiple stops
edit Route
List Route
Delete Route
|  |  |  | 2018-12-03 |  |  |  | 16/03/2018